## Growth Engine
Focus Area: Growth Engine
Actions | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Progress Midwest liaison and coordination
Concierge and liaison services | CGG, MWDC | All | Ongoing. Enquiries have been received from a proponent looking to set up a processing plant in the Midwest. CGG has assisted with the provision of land availability options. MWDC has provided contacts in JTSI. Refer to Topic Summary doc attached. | Collaboration between MWDC and CGG to facilitate Australasian Sands International (ASI) to enable 24/7 movement of sand from the extraction pit in Walkaway to the Geraldton Port. The Singaporean Housing Development Board came out of lockdown with the rest of Singapore in mid/late May 2020 and awarded CRG Contractors (ASI Singaporean tendering partner) and ASI the contract to supply 1.1Mt of construction sand over a 12 month period. In order to secure this “first of its kind contract for Western Australia, the company accepted the strict proviso that it would deliver the first 30,000 tons of Walkaway sand on a ship on 1 July 2020. ASI has been working with collectively with JTSI, DWER and MWPA to fast track all processes in order to meet the deadline. CGG facilitated the processing of all the appropriate approvals in accordance with regulations to help achieve the deadline. MWCCI liaising with ASI and lead contractor to identify ongoing opportunities for local business and employment.
Facilitate and provide managerial support to Progress Midwest | CGG | All | Ongoing. Progress Midwest COVID Impact Business Health Check survey | Ongoing.
Ongoing refinement and maintenance of the Progress Midwest website: Ensure consistency across all stakeholder websites | CGG | All | Updates on the COVID Economic and Health Information pages. | Progress Midwest website hits for financial year 2019/20 4,465 and China Connect 3,056
Agriculture and food
Food Cluster Development: Consider development of a Midwest food brand Ongoing facilitation of the Horticulture Cluster. Key priorities include: • Reliable access to water (see infrastructure) • Market research into demand for high value foods (e.g. Shanghai Hotels) •Development of summer crops • Potential for 'co-opetition' with other regions (e.g. Gascoyne for exporting; Northern Australia for bringing in exotic foods to combine with local produce for Asian tourists locally) • Potential for achieving scale for exporting through port or airport . Migrant labour . Identify Food Industry priorities for export development, capacity building and reputation growth | MWDC, DPIRD, RDA, MWCCI | MWHGG |  | MWFIC strategic planning day on 28 August 2020. The Midwest Food Industries Cluster has completed their strategic plan which informs the business case to attract FIAL funding for a 0.5FTE Executive Officer
Agriculture and food
Provide support the following initiatives for aquaculture development: • Support growth and expansion of Indian Ocean Fresh Australia (IOFA) finfish operations • Support Huon Aquaculture introduction into the Midwest via the Abrolhos Aquaculture Development Zone • Support establishment of an Australian Centre for Applied Aquaculture Research (ACAAR) led finfish hatchery at the Batavia Coast Marina Institute • Establish a Midwest Aquaculture Cluster of interested finfish, shellfish and related parties | MWDC | Industry |  | GERALDTON MARINE FINFISH INDUSTRIES: 1. Aquaculture Consulting Engineers (ACE) have completed the detailed design for the nursery equipment. 2, DPIRD compiled a request for exemption for ACE to provide and install the equipment into the facility.3.Schematic design is expected to be completed by the end of October 2020. AQUACULTURE: This update is confidential. Please contact the MWDC directly.
Southern Rangelands Revitalisation and Diversification- explore feasibility of establishing optimum station cells and support the establishment of a general purpose lease for pastoral station activities | MWDC | Southern Rangeland Pastoralists | Successful Southern Rangelands 2040 Roundtable held in Mount Magnet on 2nd October 2020 with Minister attending. The forum unanimously resolved to support the establishment of a Southern Rangelands Growers Group with the Minister announcing that DPIRD were investigating options to underwrite the establishment of the Growers Group for the first 12 months operation. | Refer to the Lead Agency MWDC
Promote local food manufacturers and producers through the ongoing updating of "A taste of Greater Geraldton" and other promotional opportunities (i.e.: Perth Royal Agricultural Show) | CGG | DPIRD MWDC MWCCI MWGAAS | CGG working with MWDC & MWCCI on the Food Cluster | CGG working with MWDC and the Food Cluster to develop this year's event. Approach will also be made to Tourism Geraldton Midwest for its involvement once funding has been secured from the Mid-West Affiliated Agricultural Societies.
Tourism cluster development
To facilitate tourism businesses in product development to gain exposure to international markets | CGG | Tourism Council WA | Proposal received from the Tourism Council of WA seeking $27K for a mentoring program to be rolled out throughout the Region. Budget currently not allocated. | Due to COVID and a reduction in the ED Budget this project will not be funded by the City.
Promote the hub and spoke tourism model and cooperate with the neighboring Shires to promote tourism | CGG | TGMW | CGG developing an online marketing campaign targeting the Perth market to visit the region once the intrastate borders open for the winter months. | Progressed as a response to the COVID crisis into the Adventure Awaits - Chase the Sun campaign. Further details see below in Implementation of Marketing Strategy.
Work with the Wind and Water Cluster to develop Geraldton as a Wind Sport destination | MWSF, Wind and Water Project | CGG MWDC Industry |  | 1. Professional Windsurfing Association Event business case developed- no funding secured.2.New strategy developed.3. Promotional video developed.4. Website developed.
Support tourism product development such: . AstroTourism . Aboriginal tourism experiences | MWDC | TGMW | Refer to Topic Summary docs provided. | MURCHISON GEO TOURISM AND ASTRO TOURISM: 1. MWDC has arranged a project management planning session for Shires and key stakeholders to provide clarity and consensus around purpose, priorities etc. for stage 2. This will help Shire CEO's make decisions regarding resourcing etc.2. Stage 1 of the Murchison GeoRegion was successfully launched on 18 September ( Mount Magnet), generating sufficient media interest and positive fedback.3. MWDC (CCF) funding acquittal is now in play.
Identify tourism data gaps and explore options to gather and collate the data | CGG | TGMW |  | No progress
Create new entry statements to Geraldton | TGMW |  |  | In progress.
Engage the citizens of the region as "ambassadors", who are well-informed about the attractions and attributes of Greater Geraldton and willing and able to promote it as a great place to live, visit, recreate and do business | CGG | TGMW |  | Various models have been explored including Northern Rivers and Townsville. The company engaged in both projects has been contacted and provided a brief. Cost estimates to be provided and then ED will need to go through CGG Executive Management Process.
Review the Geraldton Visitor Centre's role | CGG | TGMW | Underway. | Geraldton Visitor Centre was relocated to the Geraldton Regional Art Gallery on 14 September. Staffing levels have been reduced to 2.6 FTE. Savings of $400K as a result. Membership not part of the model moving forward. Booking platforms Bookeasy and Expedia remain in place earning the City commissions. Marketing materials are being developed under specific themes and itineraries are being developed. Destination marketing remains with City ED Team and also liaison with ACC/ ART/ TWA Familiarisation Unit and Tourism Council WA. GVC continues to run as an accredited Visitor Centre. The increase to foot traffic at the GRAG should assist with securing funding for the Gallery in the future. Retail space will be in place with Geraldton branded merchandise developed in conjunction with local artists. Tourism Geraldton Midwest has prioritised the taking over of the Visitor Centre in its strategic plan. A working group has been set up to facilitate this process and explore best practice operating models.
Scope and complete a unified regional Midwest Tourism Strategic Plan | MWDC | Tourism Geraldton Midwest | Refer to Topic Summary docs provided. | Strategic Plan for Tourism Geraldton Midwest finalised by MWDC.
Pursue funding and advocate for the Geraldton Museum Extension Project | MWDC | Geraldton Museum, CGG | Refer to Topic Summary docs provided. | DPIRD project management Office review of business case
Tourism cluster development
Liaison with Qantas regarding capacity and frequency of regional flights and global connections | CGG |  | Let's get Geraldton Flying again survey received 1802 responses. Report provided to Qantas, Tourism WA and DOT. | CGG leading discussion with Qantas. Ongoing discussions currently focused on increasing the schedule to best accommodate and maximize flights under the current conditions.
Abrolhos Islands Tourism Stage Two • Advocate for Abrolhos Islands access and sustainable tourism development • Support the establishment of an Abrolhos Islands cluster • Pursue funding and advocate for a jetty for high speed vessels from Geraldton to the Abrolhos Islands | MWDC | CGG, TGMW | Refer to Topic Summary docs provided. | Complete (High Speed Vessel Jetties) - State Government announced $3M commitment for two new jetties in Geraldton. $10m ABROLHOS ISLAND PROJECT.1. National park management plan due for public release end of 2020.2. FHPA and reserve management plan expected to be released in the second quarter of 2021.
Work to secure an ongoing supply commitment of crayfish into the regional tourism market | MWDC | Industry |  | Complete. Refer to attached State Government announcement.
Facilitate the further development of suitable and marketable tourism products through packaging. Consider other emerging niches e.g. First Nations, post-colonisation history, culture, nature-tell our unique and compelling stories | TGMW | Industry |  | Refer to project lead: TGMW
Raise awareness of Geraldton and the experiences on offer to grow visitation and extend stays in partnership with Australia's Coral Coast; Wildflower Country; Tourism WA and Australian Tourism | CGG | TGMW | Lobbies Tourism WA to help the region develop a Narrative for the Mid-West. Meetings currently underway. | The Tourism WA Our Narrative Workshop sponsored by the City in conjunction with Tourism Geraldton Midwest was held on July 22 2020 attracting 47 participants. Seven Mid-West Shires were represented. Results are yet to be delivered from TWA. The focus was Mid-West. Further Narrative workshops will be held within the region starting with the Wildflower Country Group.
Implement the Tourism Marketing Strategy to increase visitation and extend stays through cohesive and integrated branding and marketing of Greater Geraldton | CGG |  |  | CGG undertook an extensive destination marketing campaign (Adventure Awaits - Chase the Sun) during May to July 2020 to support the region's Tourism sector. The social media and video campaign targeted the Perth market to drive visitation north rather than south. Feedback from local businesses including restaurants, accommodation and tourism providers indicates that Geraldton was the place to be these winter school holidays! Many accommodation providers were nearing 100% occupancy throughout the July school holiday and some businesses described it as the busiest fortnight they’d ever experienced. Embracing Geraldton as the ‘hub’ to explore the whole of the Midwest region, there was a heavy push on exploring the Midwest and places such as the Houtman Abrolhos Islands, Pink Lake and Kalbarri. As part of the campaign, a series of online advertising targeting people in the south was released with more than 50,000 impressions. A collaboration with digital community Perth is OK had more than 146,000 impressions, driving people to find out more about Geraldton. Businesses were encouraged to join the campaign to help promote Geraldton, with stats from the Geraldton Visitor Centre showing 75% of people through the door were either first-time visitors to Geraldton, or hadn’t visited in more than 10 years.
Become Japan ready through delivery of cultural awareness workshops | CGG | Tourism Council | CGG staff working with the Tourism WA Familiarisation Unit. | Due to the outbreak of COVID-19 this project has been put on hold.
Fisherman's Harbor Carbon Neutral Tourism Attraction Development Project | Geraldton Fisherman's Co-op | MWPA, TGMW |  | Refer to lead agency: TGMW
Regional Tourism Conference 2021 Expression of Interest | CGG | TGMW | Geraldton has been nominated as the Regional destination for the conference in 2021. Confidential. | TCWA announced on Thursday 6 August 2020 that the City of Greater Geraldton's bid for hosting rights for the 2021 WA Regional Tourism Conference was successful. The Tourism Conference is scheduled for May 2021. A working group is to be set up led by CGG in conjunction with Tourism Geraldton Midwest to bring the event to life.
Implement the Eco Tourism Incubator Program | Pollinators | Industry |  | Not funded by Australian Government
Develop opportunities from sports tourism with Department of Local Government, Sport and Cultural Industries (DLGSC) | MWDC | DLGSC | Suggest change lead to DLGSC for this project. | DLGSC: 1. Moresby Range Conservation Park Master Plan being developed.2. Coronation Beach Master Plan being developed.3. North Midlands Trails Master plan being developed.4. Shire of Morawa ( Koolanooka Hills) Mountain Bike business case and Trails Staging Plan developed. 5. Mountain bike coach training delivered by Geraldton Mountain bike club.6. Geraldton Cycling Plan developed.7. Geraldton Cycling Advocacy Group established and several projects scoped
Develop an Events Strategy for the City of Greater Geraldton | CGG |  | Underway. | In progress.
Implement the Midwest Outdoor Recreation Strategy; Sports Tourism Strategies and other relevant plans | MWSF | DLGSC, MWSF, RDA Wind & Water Project, Geraldton Cycling Plan Working Group |  | The working group has met and confirmed the TOR and scope. The purpose is " To establish sport and recreation strategic priorities for the Midwest region to guide resource allocation and enable planning, development and advocacy initiatives". A Steering Commitee has been established and scoping documents have been prepared. The next stage is to prepare a "Consultation and Engagement Plan".
Emerging clusters
Support and facilitate opportunities with emerging industries to form clusters (e.g. niche manufacturing and suppliers to resources sector) with a view to possible expansion incorporating lessons from the pilot clusters | MWDC | Industry | Subject to MWDC available resources and other key priorities | The Midwest Food Industries Cluster has completed their strategic plan which informs the business case to attract FIAL funding for a 0.5FTE Executive Officer
;

## Quality Infrastructure
Growth engine platform for success - Quality infrastructure
Actions | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Game changer: Expansion of energy transmission | MWDC |  | Geraldton still constrained by 132KvA line from Three Springs. Opportunity to entice new industries into the region is restricted by lack of capacity, unless proponent driven and funded by other means i.e. renewable energy solutions. | Refer to MWDC Oakajee Industrial Site EOI activation topic summary update.
Game changer: Water scheme for horticulture | MWDC | MWHGG | Power and water are two key constraints for regional development. Modelling conducted by DEWR has indicated that the Allanooka aquifer is not being recharged at sufficient quantities to enable access to available water for new industry development. Alternate options for supplying water is required i.e. Desal. Some private led consortiums are investigating e.g. AGIG, but require a commercial proposition to justify investment. | The Horticulture branch of DPIRD declared that it did not want to get involved in commercial negotiations (on behalf of industry) with a Government Trading Enterprise (i.e. Water Corporation).2. DPIRD agrees to finalise a Ministerial briefing note and respond to the Geraldton Horticultural Grower's Group while the MWDC agreed to organise a meeting between growers, VEG WA and the Water Corporation.
Game changer: Carnarvon to Muchea Heavy Freight route incorporating Dongara to Northampton • Northampton Corridor Bypass • Secondary grain freight routes • Oakajee Narngulu Infrastructure Corridor • Sealing of Goldfields Highway Midwest Port Authority maximisation • Geraldton Narngulu Infrastructure Corridor | MWDC, MWPA |  | Midwest region has plentiful quantities of mining resources, but constrained from activation by non-heavy industry grade transport networks. MWDC is to establish pitch documents in support of each economic infrastructure/road priority and progress through engagement with key stakeholders to seek support for the same. Main Roads WA has commenced work to develop an Infrastructure Australia proposal for the Carnarvon - Muchea Route to enable triple road train access from Perth into the Pilbara, linking key regional towns and centres in between. This focus extends from the recently completed Perth North Link. | Carnarvon to Muchea (C2M) heavy freight/transport corridor.1. The final stage 1 Infrastructure Australia (IA) submission was presented on 28 August when nominations for the 2021 IA refresh were called.2. Infrastructure Australia notification of the satisfactory nature of the submission is expected imminently.3. The Dongara Northampton Planning study has now been signed off by the Minister for Transport and MRWA plans to hold Stage 2 Planning workshops with key stakeholders in October 2020. DONGARA-NORTHAMPTON CORRIDOR (INCORPORATING ONIC & NORTHAMPTON BYPASS). The Dongara Northampton Planning study has been signed off by the Minister for Transport and MRWA plans to hold Stage 2 site planning workshops with key stakeholders in October 2020. SECONDARY GRAIN FREIGH ROUTES: 1. Following the Federal Government's rejection of the MW2GFR submission, the request was downsized to $77,115,110 over 10 years ( including $27,910,300 high priority; $39,199,700 high/medium priority; and $10,005,100 medium priority upgrades projects).2. The Midwest Secondary Grain Freight Working Group representatives will resubmit to Melissa Price by October 12.
Game changer: City Centre headworks, land development and revitalisation | CGG | MWDC |  | BCM2 Update - Considering options to activate site by gaining access to funds set aside from transfer of Lot 601 to GASA. Development WA actioned to clarify quantum and timeframe for availability of these funds. MWDC & DWA also seeking to access residual BCM2 site environmental remediation funds to potentially combine with Lot 601 funds to build a stronger case for site development i.e. head works, etc.
Game Changer: Implementation of the Port Master Plan for the Port of Geraldton | MWPA |  |  | Draft Geraldton Port Master Plan was issued for consultation in December 2019 and the final Plan was launched by the Minister for Ports in July 2020. Projects currently in various stages of progress / Implementation include: 1) Berth 4 Strengthening (Part of Berth deck upgrade program) - Construction commencing in 2020. 2) Upgrade Port Firefighting System 3) Improve ablutions in the Fishing Boat Harbor (FBH) - new ablution block completed. 4) Tourism development in FBH - Work with industry to realise development aspirations. 5) Protect and where relevant expand the Geraldton-Narngulu Infrastructure Corridor (GNIC) - Engineering Feasibility Study and concept design underway. 6) Funding announced for Esplanade Ferry Jetty construction proposed to commence 2021.
Game changer: Investigate opportunities to make Geraldton Airport more viable | CGG |  | Consultant's Report received and is being reviewed by CGG | On hold due to COVID
Alternate Airport |  |  |  | Request through JTSI for information with regards to Pilot Academy by Japan
• Pilot Training School |  |  |  | MWPA is a proud supporter of the Alternative Training Program (APTP), an initiative which has been developed to address the declining and ageing Australian marine pilot workforce. Australia's ability to service international and domestic trade efficiently is a potential impact of insufficient recruitment and training of marine skills. The APTP allows for specialisation, leading to a career in a range of maritime related skills in the Australian workforce and results in more jobs for Australian people.
• Freight Handling
Game changer: Expansion of inter-regional aviation network | CGG/MWCCI | Regional Airlines/Qantas | On hold | MWDC: 1. Commonwealth support for regional aviation routes have been extended to March 28, 2021. 2. MWDC will participate in DOT process to access some further funding support for GET-PER.3. MWDC and other stakeholders, including the CGG, met with Aviair on August 31.
Facilitate the development of the game changer tourism attractions and infrastructure projects: • Museum of Geraldton redevelopment • Dedicated berth and cruise ship terminal at the Mid-West Port Authority • Pink Lake infrastructure • Murchison geo-tourism (stage two) • Point Moore Lighthouse Precinct | MWDC, MWPA, MWDC, MWDC, CGG | Various | Geraldton Museum - Business Case advanced, requires final economic impact assessment. Pink Lake - Heritage Study completed, no issues identified. Working group meeting to be facilitated to consider design proposals for preferred development sites. Funding source for development linked with GASA package. Murchison Geo Tourism - Business Case advanced, requires final economic impact assessment. Includes Astro Tourism as well. | Refer to MWDC topic summary docs. See also entry on Geo Tourism and Astro Tourism in the Growth Engine section. PINK LAKE masterplan in progress. MWPA - Dedicated berth and cruise ship terminal included in Port Master Plan. MPWA - Esplanade Ferry Jetty to support Abrolhos Tourism is in progress.
Game changer: Geraldton Hospital redevelopment | WACHS | MWDC, MWCCI, RDAMWG | MWCCI promoting through state priorities (newsletter & media) | In progress
Facilitate a coordinated approach to the development of an "Import and Export Logistics Hub" through collaboration with relevant agencies, proponents and logistics companies | MWPA | MWDC, M WCCI, RDAMWG |  | Collaborating with MRWA on Infrastructure Australia submission to enable RAV10 access between Carnarvon and Muchea. MWPA is supportive of the proposed Dongara to Geraldton to Northampton Corridor.
Staged development of Oakajee Industrial Estate | MWDC | Development WA JTSI | Working with Min's office around advice of needs for site activation i.e. ONIC, etc. | Oakajee EOI process launched on September 18, Closing December 24.2. MWDC hosting a working group with JTSI, DWA and MWPA through process.3. Project scope and project management supports to be developed with DPIRD project management Office
Inland Port Narngulu and associated infrastructure | MWPA | CGG, JTSI, Development WA |  | GNIC Engineering Feasibility Study and Concept Design is underway. MWPA continues to promote Narngulu to potential proponents where on-Port storage is not available or feasible.
Support Midwest metal mining and non-metal mining proponents to establish the commercial feasibility of respective projects for export from the Midwest | MWDC |  | MWDC continues to engage with a number of new industry proponents across the energy and resources sector. Some progress being experienced with renewable hydrogen projects. | Refer to MWDC topic summary doc.
Midwest DigiFarms Project- Support deployment of enterprise grade internet connectivity via a wireless network throughout Midwest grain growing areas | MWDC | CGG | Chapman Valley and Northampton sites 90% complete and coverage has been extended by farmers seeking access outside of the initial area. North Midland sites are around 60% complete. Good take up of the service, particularly given COVID19 events. | Take-up in Northampton/Chapman Valley has been excellent due to the shires and grower groups promoting the availability of service, but take-up in North Midlands has been below expectations, due to insufficient promotion by the shires and grower groups, which could be improved.
Data Fibre Backhaul- Scope project to roll out digital fibre across the main highway network in regional WA | MWDC |  | DPIRD working with one preferred proponent around a proposal. Project may present some commercial viability challenges. | Project deferred due to lack of commercial viability.
Engage with state government planning agencies to advocate for an east west corridor for future Midwest regional freight movements | MWDC | CGG | Project yet to commence, not prioritised by MWDC Board. | Carnarvon to Muchea (C2M) heavy freight/transport corridor.1. The final stage 1 Infrastructure Australia (IA) submission was presented on 28 August when nominations for the 2021 IA refresh were called.2. Infrastructure Australia notification of the satisfactory nature of the submission is expected imminently.3. The Dongara Northampton Planning study has now been signed off by the Minister for Transport and MRWA plans to hold Stage 2 Planning workshops with key stakeholders in October 2020.
Enable development of renewable energy and secure power supply: • Energy green hydrogen emerging as a high government priority- potential to create opportunities for the Midwest • Advocacy around green energy production, storage; transmission and export capacity • Community energy (note this has potential to also reduce leakage out of the local economy) | MWDC |  | Significant proponent driven activity in renewable hydrogen. Two key announcements made. Further confidential update to be provided at the meeting. | Refer to attached topic summary doc.
Pursue the Mullewa Hospital Development | CGG | MWDC |  | No update
;

## Investment attraction
Growth engine platform for success - Investment attraction
Actions | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Proactively match markets and investors with local clusters and businesses, focusing on China whilst scanning for new opportunities through the China Connect website | CGG | MWPA, MWDC | Ongoing | Ongoing
Investigate opportunities for new strategic relationships | CGG | MWPA | Ongoing | Ongoing
Liaise with private and government organisations to provide support to projects that result in wide reaching economic benefits and attract trade and investment | CGG | MWCCI, MWDC, RDAMWG MWPA | Refer to Regional Priorities | Progress Midwest and CGG Priorities have been distributed to all parties. CGG and MWCCI to meet to progress promotion of state priorities
Leverage the Department of Primary Industries and Regional Development "Living in the Regions" campaign to promote Geraldton | CGG | MWPA, MWDC | No communication has been received from DPIRD | No further communication on this initiative has been received from DPIRD.
Identify, promote and activate economic development opportunities through existing sister city and strategic partner relationships | CGG |  | Ongoing | Ongoing through China Connect
Facilitate and coordinate (in collaboration with other agencies) inbound business delegations to Geraldton and the Midwest with an emphasis on those delegations considering potential investment and/or trade opportunities | CGG | MWPA, MWDC | On hold | On Hold
Participate in/present at relevant investment forums, trade shows and conferences | CGG |  | On hold | On Hold
Identify and promote potential sites and opportunities within the Midwest with higher use investment potential (i.e. Geraldton Airport Technology Park) | CGG | MWDC, MWCCI, RDAMW, MWPA |  | Ongoing
;

## Healthy circulation
Focus area - Healthy circulation
Actions |  | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Business events and facilitation to better connect Geraldton businesses to each other to increase local B2B procurement |  | MWCCI | All Stakeholders |  | Regular business networking events have resumed. All event details and registration can be completed through. https://mwcci.com.au/events/#!calendar Summit planning with Mid-West Food industry dinner in planning for 1 and 2 December 2020
Development of a Mine Resourcing Policy |  | CGG |  |  | Completed. Council Policy 2.6: Mine Resourcing
Mining procurement project to better link local suppliers and workforce (Geraldton and across the region) with the needs of the resources sector |  | RDAMWG | MWCCI, CGG, MWDC | Ongoing discussions with Chamber of Minerals & Energy. Pilot project with Meekatharra Industry Group to link local traders with resource companies. | On additional update.
Engage Murchison Local Government Authorities and new/expanding Midwest miners on opportunities to use Geraldton as a FIFO Hub, whilst maximising economic and social opportunities for host communities |  | MWDC | MWCCI, CGG | Project deferred as a MWDC priority, with preference to METS project. | MWDC.1. Rio Tinto Refurb, servicing and rebuild. Negotiations between Rio Tinto and Westrac continue for the initial trial.
Develop a Midwest Regional Benefits Package (in business case format) to leverage SKA infrastructure investment to maximise economic development opportunities (including Aboriginal economic development opportunities) in the space economy |  | DIIS | MWDC |  | MIDWEST SPACE ECONOMY REGIONAL BENEFITS PACKAGE.1. The Australian Government ratified the Square Kilometre Array (SKA) Observatory Convention on 29 September 2020. The observatory will be responsible for delivering the SKA.2.MWDC's space economy regional benefits package has been submitted to DPIRD and is being externally assessed before being submitted to the Minister for a funding decision..3.MWDC is providing input in to the State-Federal SKA Collaborative Agreement and Projects Agreement, to ensure the regional benefits agenda is captured in the agreements.
Develop and implement a "Buy Local campaign" which includes a focus on product quality and customer service | pa d implement a "buy local campaign" which includes a focus on product quality and service | CGG | MWCCI | Geraldton is Open for Business Website page and ongoing social media platform campaigns. | Progressing in collaboration with MWCCI and subject to the outcome of the extended funding application to RIO Tinto
Develop an MOU between Chamber of Minerals and Energy and Progress Midwest to provide partnerships, collaboration and procurement opportunities for local Midwest businesses through mining companies | pan MOU between Chamber of Min s nergy and Progress Midwest to provide rships, collaboration and procurement opportunities for local Midwest businesses through companies | RDAMWG | CGG, MWDC, MWCCI |  | To date two meetings held with CEO, CME with representatives of MWDC, CGG, MWCCI, RDAMWG. Most recent meeting Tuesday 4th Aug. discussed support for METS Pilot & emergent supply chain initiatives. CME pointed out increased targets for local sourcing (20%) & skill and labour shortages for the resources sector.
Establish Geraldton and the Midwest Region as a rebuilt and refit centre for supporting mining operations in the Northwest- Midwest Equipment Repair and Rebuild Project (METS} |  | MWDC | CGG, MWDC, MWCCI, RDAMWG, | Refer to topic summary update. | RIO TINTO REFURB, SERVICING & REBUILDS.1. Negotiation between Rio Tinto and Westrac continue for the initial trial.2. Ongoing MWDC project management resourcing support will need to be identified
j,
Re-promote the "Leakage Study" findings within the business community |  | CGG | MWCCI | On hold | On hold
Investigate migration attraction/visa programs |  | RDAMWG | CGG, MWCCI, MWDC | Under review | Under review
Improve youth transitions from school to training, further education or work, including better utilising the VET and school-based apprenticeship and traineeship system to link youth with industry, as well as a focus on developing employability skills for youth in the 18-22 age bracket |  | CRTAFE? | MWPA |  | MWPA collaborates with local Midwest schools to deliver industry relevant curriculum. In 2020, MWPA worked with the Australian Corrosion Foundation to deliver the "All at Sea" program to three local high schools. Students simulated and tested which environmental conditions influence the rate of corrosion of different metals and described the observed changes in a six-part lesson plan which culminated with a tour of the Geraldton port. MWPA aims to build youth awareness of port industry operations, its environment and challenges, and further career opportunities in our region.
Support announcement and implementation of regional initiatives contained in the Geraldton Aboriginal Settlement Agreement |  | MWDC |  | Refer to topic summary update. | GASA Pink Lake and Lucky Bay Infrastructure.1. MWDC continues to participate in a range of stakeholder meetings in regards to the ILUA.2. Pink Lake Masterplan to be finalised.

## Innovation and entrepreneurship
Growth engine platform for success - Innovation and entrepreneurship
Actions |  | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Expand and leverage the region's considerable knowledge assets in higher education, research and technology: |  | GUC, MWDC | MWPA | See bullet points below | See bullet points below
• Research and development network |  |  |  | GUC: Midwest Research and Development Network established to link universities/researchers and local industry to address regional research and development priorities. Members include GUC, CSIRO, CRTafe, Rob Jefferies & Assoc, WA Centre for Rural Health and MWDC. AMOG/ MWPA Mets Ignite Project - Federal Funding obtained for Wharf Alert/ Load Alert Project. | Business Case complete for Midwest R & D network.Linked to MWDC Leverage Fund submission seeking resources to scope up a SKA Regional Benefits Package, incorporating a resourced Mid-West R&D Network.
• GUC expansion and development of universities partnership |  |  |  | GUC extension is complete providing 24/7 study access for students. New partnership with Curtin University is now established adding Agribusiness and Indigenous Tertiary Enabling Course to GUC's offerings. | Complete
• Establish SKA Regional Benefits Package to leverage SKA infrastructure investment |  |  |  |  | The Australian Government ratified the SKA Observatory Convention on 29 September 2020. MWDC's space economy regional benefits package has been submitted to DPIRD and is being externally assessed before being submitted to the Minister for a funding decision. MWDC is providing input in to the State-Federal SKA Collaborative agreement, to ensure the regional benefits agenda is captured in the agreements. GUC and CSIRO have entered into negotiations for a sublease on the GUC site to build an Engineering Operations Centre to service the SKA project. 45 permanent jobs to be created.
| Pollinators Base Camp Incubator | POL |  | Successfully delivered first cohort through the program early 2020. Second phase is in partnership with Meshpoints. Program is delivered in two parts - the first delivered by Meshpoint. The second part delivered by Pollinators - mentoring and support post 8 week Meshpoint program. | Currently delivering the reduced Base Camp 2. There are approximately 8 Midwest participants, covering a range of concepts. Meshpoints and PlusEight accelerator have supported the participants in the program.
| Implementation of Midwest Innovation Agenda | POL |  | Requires government support and investment for implementation actions to be progressed. | WA Regional Innovation Summit was delivered in Geraldton on the 18 September by DPIRD. Pollinators Inc. is awaiting a summit report and further comments from government. Pollinators is finalising a maturity report, which indicates early stage maturity and some possible pathways forward.
Ongoing collaboration with Mesh points |  | POL |  | Pollinators is part of the Meshpoints Practitioner network. Actively working with Meshpoints on Basecamps, and advocacy roles. | Ongoing
Pursue the establishment of a new Midwest Innovation and Business Enterprise Hub (including co­ location of Pollinators and the Mid-West Chamber of Commerce and Industry) to further grow the regional innovation eco-system |  | POL, MWCCI |  | Requires state government funding to progress | Continuing to pursue
;

## Economic participation
Growth engine platform for success - Economic participation
Actions | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Support the establishment and development of local Aboriginal businesses | MWDC | MWCCI | Refer to topic summary update. | MWCCI Working Together has been confirmed for ongoing funding for another 2 years. Recruitment of new coordinator underway. MWDC: ABORIGINAL BUSINESS 1.Aboriginal Capability Funding applications have closed.2.Involvement in Aboriginal Businesses in Housing project (SHERP).3. Noongar CCI and review of the Aboriginal Procurement Policy.
Skills development for clusters with a focus on food (horticulture and aquaculture), marine trade and support services, and tourism and any clusters added | GUC | TAFE, MWDC, Industry | Assoc Degree in Agribusiness commenced at GUC | Curtin University Associate degree in Agribusiness running at GUC
;

## Positive reputation
Growth engine platform for success - Positive reputation
Actions | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Assist with business retention and growth | CGG | MWCCI | Geraldton Open for Business Website page and ongoing promotion through social media platforms | ‘The Geraldton is Open for Business’ page on the City’s website provided the opportunity for businesses to register their information in adapting their operations during the pandemic. Almost 100 businesses registered. To support these businesses the City ran a social media campaign promoting each business listed in an effort to get our community to support local businesses. Some of these posts had businesses reporting inquiries from the eastern states for their products. In addition, the City website now contains a COVID-19 Business page providing all the relevant information and links for local businesses to access.
Create a Geraldton identity and promote Geraldton as one of Australia's most desirable places to live, work, study and play to overcome lack of profile or negative profile. (Relocation guide and #makethemove campaign) | CGG | MWPA | Video has been produced and distributed through MWCCI members. Further campaign development required. | MWPA have prepared numerous videos promoting working at the Port and have feature articles in the following publications: 1) Daily Cargo News 2) The Australian 3) Shipping Australia Magazine 4) Port Australia 5) MIAL 6) The West Australian
Attract and support the establishment of new businesses or the relocation of existing businesses from other areas (i.e.: working with Franchise Council Australia) | CGG | MWPA | On hold. | New Trades to the Port - Australasian Sands International Pty Ltd (Construction sands exported to Singapore) and Iluka Mineral Sands Concentrate exported to Asia. At least three other exporters are considered imminent.

## Strong heart
Focus area - Strong heart
Actions | Lead | Partners | Progress update Mid 2020 | Progress update October 2020
Develop Place Management Plans for Rocks Laneway and support activation of the Laneway | CGG | The Geraldton Project | Completed | Roks Laneway Activation project commenced again October 2020
Finalise the Vibrancy Policy and Strategy for the City Centre | CGG |  | Completed and going to May 2020 Council Meeting. | Endorsed by CGG Council May 2020
Create a City-led initiative to encourage landowners that back onto Foreshore Drive to redevelop or re-orient their buildings to face the Geraldton Foreshore | CGG | Landowners /CCAG | On Hold | On Hold due to COVID-19
Introduce interim pop-up uses to activate vacant areas and buildings to encourage innovation and entrepreneurship- subject to land owners' expectations | CGG | The Geraldton Project | On Hold | On Hold due to COVID-19
Develop and introduce a city centre Marine Terrace brand ("The Terrace" concept) | CGG | CCAG/ The Geraldton | On Hold | On Hold due to COVID-19
Advocate for funding for the Geraldton Gateway Project | CGG |  | Refer CGG Election Priorities | Refer to CGG Election Priorities